TRILLET · WHITE-LABEL CLUSTER

4-Week Sprint Plan

A compressed, honestly-sized plan for the white-label cluster, 14 Sep - 11 Oct 2026. Task timing follows real effort, not round numbers: the metadata and redirect work is hours and ships immediately; content is the only real constraint and sets the four-week length. Six new white-label blogs (the gaps against Insighto) are folded in.

What makes four weeks real Assumes ~1 developer + ~1.5 content writers working focused. With less, the four broad listicle blogs slip first — they are reach plays, lower intent. The audit is done. Snippets and redirect configs are hours of work, so they ship in Week 1 rather than being spread out. The extra index hubs (/compare, /industries, /academy, /reviews) are cut — not required for the core fix. Listed as deferred, not padded in.

Task sizing (the sanity check)

Real effort per task, and why it lands where it does. Small tasks are not stretched to fill weeks.

| Task | Real effort | Note | Week |
| --- | --- | --- | --- |
| Snippet rewrites — 17 pages | ~0.5 day | Copy already written in the CTR worklist; paste into CMS. Not a multi-week job. | W1 |
| Structured data + self-canonicals | 1-2 days | Org / WebSite / SoftwareApplication / FAQ, sitewide templates. | W1 |
| Baseline metrics snapshot | 0.5 day | Freeze the before-numbers. | W1 |
| Redirect configs — 22 | ~0.5 day total | Trivial to configure. Risk, not effort, forces the two waves. | W1 + W3 |
| /whitelabel hub rebuild | 4-5 days | The long pole. Content + design. | W1→W2 |
| 6 new white-label blogs | ~1 day each | 1,500-2,500-word guides / roundups. | W1-W3 |
| 6 P1 on-page rewrites | ~0.5 day each | Expand & restructure existing blogs. | W2-W3 |
| 2 chatbot reframes | ~0.5 day each | Rewrite to voice framing. | W2 |
| Content merge for Wave 2 | 3-4 days | Fold unique content of heavy sources into targets before redirecting. | W2 |
| /integrations/gohighlevel landing | 1-2 days | Must exist before the GHL redirect. | W2 |
| /partners reseller hub | 2-3 days | Consolidate 3 invisible pages + real program content. | W3 |
| Internal-linking pass | 1-2 days | Wire blogs + new content up to /whitelabel and /partners. | W3-W4 |

Totals ≈ 24 content person-days + ~5 dev-days across four weeks. That is the resourcing the schedule below assumes.

The four weeks

| Week | What ships | Gate / check |
| --- | --- | --- |
| W1 14-20 Sep | • Dev: all 17 snippet title/meta rewrites live (P0+P1+P2 — copy is ready). • Dev: structured data + self-canonicals sitewide. Freeze baseline. • Dev: fire Redirect WAVE 1 — 9 pages, <1k impr (dead/low; little or no content to merge). • Content: /whitelabel rebuild — draft. • Content: publish Blog 1 (White-Label Partnerships: Complete Guide) + Blog 2 (Best White-Label Reseller Programs 2026) — both feed /partners. | Baseline frozen; Wave-1 301s verified |
| W2 21-27 Sep | • Content: publish the rebuilt /whitelabel hub. • Content: publish Blog 3 (White-Label SaaS Platforms) + Blog 4 (White-Label Tools for Agencies). • Content: merge Wave-2 sources into targets; rewrite the 2 chatbot reframe pages. • Dev: build /integrations/gohighlevel (before its Wave-2 redirect). | Wave-1 health check |
| W3 28 Sep-4 Oct | • Dev: fire Redirect WAVE 2 — 13 pages, ≥1k impr (incl. the 44k / 18k / 16k pages). Publish chatbot reframes. • Content: 6 P1 on-page rewrites; /partners reseller hub (consolidate /reseller, /oem, /referral + content). • Content: publish Blog 5 (Best AI White-Label Services) + Blog 6 (White-Label Digital Products). • SEO: internal-linking pass begins (blogs + new content → /whitelabel, /partners). | Wave-2 301s verified |
| W4 5-11 Oct | • SEO: finish internal linking; orphan sweep + link QA. • Dev: /integrations directory (light) if capacity allows. • CHECKPOINT: early CTR read (snippets, ~3 wks); Wave-2 health; /whitelabel head-term movement; programme review. | End-of-sprint review |

The 6 new white-label blogs (Insighto gaps)

Topics Insighto ranks for and Trillet has zero of — the top-of-funnel discovery layer above voice-AI-white-label. Prioritised so the two that feed the invisible /partners funnel go first.

| # | Blog | Targets / gap | Funnel role · week |
| --- | --- | --- | --- |
| 1 | White-Label Partnerships: The Complete Guide | "white label partnerships" — informational pillar; Trillet: none | → /partners · W1 |
| 2 | Best White-Label Reseller Programs 2026 | "white label reseller programs" — broad roundup; Trillet: voice-only | → /partners, /whitelabel · W1 |
| 3 | Best White-Label SaaS Platforms to Resell 2026 | "white label saas" — broad, high volume | → /whitelabel · W2 |
| 4 | White-Label Tools for Agencies: 2026 Stack | "white label tools for agencies" — Trillet: none | → /whitelabel · W2 |
| 5 | Best AI White-Label Services to Resell 2026 | "ai white label services" — Trillet: voice-specific only | → /whitelabel, /partners · W3 |
| 6 | Best White-Label Digital Products to Sell 2026 | "white label digital products" — Trillet: none | → /whitelabel · W3 |

These are listicle/guide formats — they name other tools/categories, which is standard on a blog (not the homepage): Trillet is the featured pick, leading with compliance and the auditable record. They trade higher reach for lower voice-AI intent than the existing high-intent pages.

Redirect waves (22, in two gated waves)

| Wave | Fire | Pages | Contents |
| --- | --- | --- | --- |
| WAVE 1 | W1 | 9 | <1k impr — dead & low, little/no content to merge. Validates the mechanics safely. Incl. how-do-white-label-chatbots-work, voice-ai-architecture-native-vs-wrapper, ai-chatbot-agency-business-model, monthly-revenue-breakdown, voice-ai-vs-text-ai-for-customer-service, ghl-v3-native-ai-vs-dedicated, how-much-money-can-you-make, white-label-ai-profit-margin-analysis. |
| WAVE 2 | W3 | 13 | ≥1k impr — content folded into targets in W2 first, fired after Wave 1 is verified. Incl. the heavy hitters: best-white-label-ai-chatbot-for-agencies-2026 (44k), gohighlevel-voice-ai-integration (18k → /integrations/gohighlevel), what-is-white-label-ai-chatbot (17k), ai-receptionist-white-label-pricing (16k), white-label-ai-chatbot-pricing-comparison (14k), + 8 more. |

Two waves, not three — four weeks does not allow three gated checkpoints. Rollback rule: if a 301 doesn't resolve or a target loses material ranking, pause and diagnose before continuing. If content capacity is tight, the heaviest Wave-2 merges can slip a few days into W4 without breaking anything.

Cut from scope (deferred, not dropped)

- Index hubs — /whitelabel/compare, /industries, /academy, /reviews. Structural nice-to-haves; the internal-linking pass covers the same authority routing for now. Build post-sprint.

- The 2 chatbot REFRAME pages stay as reframes, not redirects — they hold real query demand; rewriting to voice framing keeps it.

Honest risks

- Content is the bottleneck. ~24 content-days in four weeks needs real writing capacity. Short on it, cut Blogs 3-6 first (lower intent) — never the hub rebuild or the merges.

- Tighter redirect gating. One week between waves gives partial reindex signal. The rollback rule matters more at this pace.

- The W4 review is a direction read, not a result. Consolidation ranking gains take 4-8 weeks; the real read is ~mid-to-late October. Snippet CTR moves faster and should show first.